## Slide 1
GLOBAL BROADBAND HEALTH DASHBOARD
AZURE MIGRATION PROPOSAL
Prepared for: Accenture
Date: 7/19/2020
Notes: Drag Picture and Send to Back

## Slide 2
CONTENTS
Project Background – What we heard?
Proposed Approach
Technical Architecture
Estimates
Next Steps

## Slide 3
WHAT WE HEARD
MIGRATE TO AZURE ANALYTIC SERVICES
NEED TO BE IN PRODUCTION BY APRIL 2021
GBHD PROJECT BACKGROUND - WHAT WE HEARD
NEED SUPPORT (AZURE) TO AUGMENT INTERNAL CAPACITY AND PROCESS SMEs
EVOLVE FROM HISTORICAL DASHBOARD TO PREDICTIVE BROADBOND CONSUMPTION USAGE
Notes: To be more predictive about the WAN and wireless consumption.

## Slide 4: CAP To Azure – FY21
 | Q1 – FY21 |  |  |  |  |  |  |  |  |  |  |  | Q2 – FY21 |  |  |  |  |  |  |  |  |  |  |  | Q3 – FY21 |  |  |  |  |  |  |  |  |  |  |  | Q4 – FY21 |  |  |  |  |  |  |  |  |  |  | 
Work Area | Sept |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  | 
Data Lake Build
CAP Migration - GBHD
Cloud 1.0 - Wireless
Legend:
On schedule
Minor Delay
Completed
Major Delay
Not Started
Milestone
Data Lake Ready
Data Ingestion
CAP Migration Complete
PulseSecure
DLC
IPAM
New Ingestions + PoCs Envs.
Ingestions – Event Grid
From CAP to Azure LitC
CAP Migration
IP Address Mapping and Chargeback
Visualization
Data Ingestion
Visualization
Transformation
UAT
UAT
CAP Migration - SNOW
Data Ingestion
Visualization
Transformation
UAT
Transformation
Incident Mgmt
Change Mgmt
Problem Mgmt
Incident UAT
Change UAT
Problem UAT
RITM
RITM UAT
Firewall UX UAT
Firewall UX
UAT
UAT
UAT
Viz Upg - SNOW
Viz Upg - Pulse
Viz Upg – Device LC
Viz Upg - IPAM
IPAM/Logs TBD
UAT
UAT
Pilots
Viz - Upgrade
Data Ingestion
Transformation
UAT
UAT
Critical Applications need to move out of CAP by March 2021

## Slide 5: Project Resource Estimates CAP and Cloud 1.0 to Cloud 2.0 (Azure) Migration
Payroll - Expense Description |  | FTE - FY21 |  |  |  |  |  |  |  |  |  |  | 
Resource Enterprise ID / TBD | Resource Type | SEP 2020 | OCT 2020 | NOV 2020 | DEC 2020 | JAN 2021 | FEB 2021 | MAR 2021 | APR 2021 | MAY 2021 | JUN 2021 | JUL 2021 | AUG 2021
PM | 8-Consultant | 1 | 1 | 1 | 0.75 | 1 | 1 | 1 | 0.5 | 0.5 | 0.25 | 0.25 | 
Microsoft SME | 9-Consultant | 0.5 | 1 | 1 | 0.5 | 1 | 1 | 1 | 0.5 | 0.5 |  |  | 
Developer | 10-Analyst - | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 
Data Engineer | 10-Analyst | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 
Visualization | 10-Analyst | 2 | 3 | 3 | 1.5 | 3 | 3 | 2 | 1 | 1 | 1 |  | 
Data Arch. | 9-Consultant | 0.5 | 1 | 1 | 0.5 | 1 | 1 | 0.5 | 0.5 |  |  |  | 
Operations | 10-Analyst |  |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
Resource Plan - Total |  | 7 | 9 | 9 | 4.75 | 9 | 10 | 8.5 | 6.5 | 5 | 4.25 | 3.25 | 1
Start Date Sep 2020
Applications in Scope :
  Global Bandwidth
  ServiceNow and
  IP Address Mapping
  Cloud 1.0 Applications / Dashboard
70% of resources will be focused on CAP Migration and 30% on Cloud 1.0 migration

## Slide 6
PROPOSED APPROACH

## Slide 7
ENGAGEMENT PHILOSOPHY
TOOLS
TALENT
DISCOVERY
CONVERSION
MIGRATION
SYNCHRONIZATION
ANALYSIS
IMPLEMENTATION
MODERNIZATION
OPTIMIZATION
TEAMING
COLLABORATE WITH CLIENT SMEs
DEFINE SUCCESS CRITRIA
REMOVE IMPEDEIMENTS
KNOWLEDGE SHARING

## Slide 8
PHASED DELIVERY APPROACH
Discovery Phase
AUTOMATION AND VALIDATION PHASE
RELEASE
1-3 Weeks
Backlog, Non Functional Requirements,
Capture Benchmarks
Release Planning
2 Weeks Sprinting
Backlog refining
Azure Data lake, Databricks in place
IMPLEMENTATION PHASE
Automate pipelines with Azure DevOps
Production planning and hardening
Documentation and Enablement
Integrate the downstream applications
Integrate Power BI, Qlik
Integration testing and UAT
INTEGRATION AND TESTING
Production Release
Data processing on Azure Databricks
Notes: Can we share previous experience with such work (Hortonworks to Azure Databricks)?
PILOT PHASE – SUCCESS CRITERIA
ADD EXTRA SLIDE – NEXT STEPS (RIGHT AT THE END)

## Slide 9
TECHNICAL ARCHITECTURE

## Slide 10
FUTURE STATE ARCHITECTURE
Volume and THROUGHPUT
Volume
  200 GB Hive warehouse
  <100 Users
Pain Point
  4-5 weeks to renegotiate the contract
Faster Contract Negotiation
  Takes 4-5 weeks to renegotiate the contract under current setup
Azure Functions
= Proposed Azure Service for GBHD

## Slide 11
CURRENT VS FUTURE STATE MAPPING
Hadoop HortonWorks
Azure Databricks
HiveQL
Azure Databricks
Spark
Azure Databricks
HDFS
ADLS 2/ (Synapse Optional)
Talend
Azure Data Factory
Control M
Functions \ Azure Batch
Notes: Synapse – Add that in the future state

## Slide 12
ESTIMATES AND TIMELINE

## Slide 13
TIMELINE - GBHD
Roadmap & Schedule
**SCOPE:
Azure Databricks setup / configured for data processing
Integrate EBI Jobs to Data Lake
Migrate the Data to Azure Data Lake Gen 2
Migrate from HiveQL to SparkSQL
Migrate all Talend jobs to Azure Data Factory
 | WORKSTREAM | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY
Phase 1 | Discovery (1-3 Week) |  |  |  |  |  |  |  |  |  | 
 | Implementation (Azure Data Lake) |  |  |  |  |  |  |  |  |  | 
 | Databricks Implementation |  |  |  |  |  |  |  |  |  | 
 | Automation |  |  |  |  |  |  |  |  |  | 
 | Data Migration |  |  |  |  |  |  |  |  |  | 
 | UAT / Go Live Ready |  |  |  |  |  |  |  |  |  | 
Phase 2 | ML Modeling |  |  |  |  |  |  |  |  |  | 
 | Data Visualization |  |  |  |  |  |  |  |  |  | 
Databricks, Jobs, Scripts
Discovery
Data Lake
UAT
Predictive
Data Visualization
Dev Ops
Go Live Ready
Data Migration
Notes: Lift and Shift – look for the Data engineering efficiency. Predictive Modeling be ph-2

## Slide 14
ACCENTURE RESOURCES - REQUEST
ROLES | ACTIVITIES | HOURS / COMMITMENT | WEEKS / UNITS | EST. HOURS
Technical Architect | Understanding exiting HortonWorks setup, Data Processing, Control M, Enterprise Automation standard, review, Static/ Dynamics Security code review, reviewing and approving architecture and Knowledge Transfer | 5 | 20 W | 100
Technical SME | Current Dashboard, Control M/ Schedule Job specific understanding (Backlog), Technical design, Integration points etc. | 20 | 6 W | 120
Sponsor (Yakuta Rasheed) | Dev Manager / Technical Product Owner | 5 | 20 W | 100
Infrastructure Engineer | Firewall rules, User Access, IP Ranges, creating Azure access points, Security Key Generation, Certs, available domain names, Network Architecture, Data Security, reviewing and approving architecture and changes | 20-30 | 1 | 20-30
Qlik Engineer | Integration with Databricks for Qlik apps | 20-30 | 1 | 20-30
EBI Engineer | Integration with ADLS/ ADF | 20-30 | 1 | 20-30

## Slide 15
PROPOSED NEUDESIC TEAM
Development
Leadership
DELIVERY MANAGER
TECHNICAL ARCHITECT
DATA ENGINEER
devOps/ Testing
DEVOPS ENGINEER
DATA ENGINEER

## Slide 16
NEUDESIC SERVICES ESTMMATE
SCHEDULE
18-20 WEEKS
NEUDESIC TEAM
PART-TIME RESOURCES:
ENGAGEMENT MANAGER
TECHNICAL ARCHITECT
DEVOPS ENGINER
FULL-TIME RESOURCES:
SR. DATA ENGINEER (2)
DELIVERABLES
AZURE DATA PLATFORM
INGESTION SCRIPTS
TRANSFORMATION SCRIPTS
INTEGRATION WITH DOWNSTREAM APPs
BUILD, RELEASE PIPELINE AUTOMATION
ESTIMATED COST
MVP: ~$175-$200K
*MICROSOFT INVESTMENT: TBD

## Slide 17
Neudesic @ Accenture
Neudesic team executed a successful project with Accenture (Chella Murugapan) to migrate their AWS applications to Azure. The responsibilities included to assess and migrate the applications from.
Tasks included recommendation and implementation of environment configuration, AWS Lambda to Azure Functions porting, security, logging, authentication and rewriting the code as per the recommendations. Following was achieved
All task related to the architecture, implementation, coding, testing completed
Knowledge transfer was completed to train the Accenture support team to support the future work on these application
Documentation and backlogs were provided
4. Regular demo/ and status were provided through out the project

## Slide 18
NEXT STEPS
Finalize plan: approach, scope and deliverables
Confirm technical architecture and pilot phase priority (define success criteria)
Identify (Accenture) team / resources and confirm commitments and availability
Resource (Neudesic) onboarding
Project Kickoff: August/ September?

## Slide 19: THANK YOU!